# Project Status Report

[Project name]  |  Report date: [date]  |  Period: [weekly / monthly]

# 1. Project Details

| Project name | Website Redesign |
| --- | --- |
| Project manager | Maya Chen |
| Sponsor | Daniel Ortiz, VP Marketing |
| Current phase | Build |
| Percent complete | 52% (plan: 60%) |
| Budget | $120,000 total, $70,000 spent, forecast $134,600 |

# 2. Overall Status and Summary

Overall status rule: any Red area makes the project Red; any Amber makes it Amber; otherwise Green. Keep the summary to 2 to 4 sentences.

| Overall status | Summary: where we are, what changed, what we need |
| --- | --- |
| AMBER | The redesign is 52% complete against a plan of 60%. Content migration is one week late because product pages need legal review. Budget is tracking slightly over. We need a decision on the launch date by Friday. |

# 3. Health by Area

| Area | Status | Notes and recovery action |
| --- | --- | --- |
| Schedule | Amber | Content migration 1 week late. Contract writer added to catch up. |
| Budget | Amber | Writer adds $6,000. Covered by the 10% contingency. |
| Scope | Green |  |
| Quality | Green |  |
| Resources | Amber | Lead developer out 3 days next week. |

# 4. Milestones

| Milestone | Due date | Status | Comment |
| --- | --- | --- | --- |
| Design approved | [date] | Done |  |
| Content migrated | [date] | Late | 1 week |
| User testing | [date] | Not started |  |
| Go live | [date] | Not started |  |

# 5. Progress This Period

| Done this period | Planned for next period |
| --- | --- |
| Built 14 of 16 page templates | Finish the last 2 templates |
| Moved 120 of 210 pages to the new CMS | Clear legal review on product pages |
|  | Book 8 users for testing |

# 6. Risks and Issues

| Type | Description | Impact | Owner | Action |
| --- | --- | --- | --- | --- |
| Issue | Legal review is slowing product page migration | High | Maya Chen | Daily 15-minute review slot agreed with legal |
| Risk | Search rankings may drop after launch | Medium | Sam Lee | Map 301 redirects for all old URLs before go live |

# 7. Decisions or Help Needed

If the overall status is Red, always ask for a decision or help here.

| Decision needed | From | By |
| --- | --- | --- |
| Keep the launch date or move it 1 week | Daniel Ortiz | [date] |

# 8. Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project manager |  |  |  |
| Sponsor |  |  |  |