## How to Use
Project Status Report Template
Free template from ProjectManagers.net
How to fill it in
1. Open the Status Report tab. Type only in the cream cells. White cells hold formulas.
2. Set the report date, planned % and actual % complete, budget and spent to date.
3. Pick Green, Amber or Red for each health area and write what you are doing about every Amber or Red.
4. Overall status is calculated: any Red makes it Red, any Amber makes it Amber, otherwise Green.
5. List milestones. Rows past their due date that are not Done are flagged OVERDUE in red.
6. Add risks and issues with an owner and an action. Rows missing either are highlighted.
7. After each report, add one line to the Trend tab so the sponsor can see the direction, not only today.
Suggested color rules (used in the Suggested cells)
Schedule: Green if actual % is within 5 points of plan, Amber within 15, Red beyond 15.
Budget: cost index = (budget x actual %) / spent. Green at 0.95 or more, Amber at 0.85 or more, Red below.
The example row values (Website Redesign) show the expected format. Replace them with your project.
Need a full report online? Use the free Status Report Builder on projectmanagers.net/5-free-project-status-report-templates/

## Status Report
Project Status Report
Cream cells are inputs. Example values: Website Redesign. Template by ProjectManagers.net
PROJECT DETAILS
Project name | Website Redesign |  |  | Planned % complete | 60%
Project manager | Maya Chen |  |  | Actual % complete | 52%
Sponsor | Daniel Ortiz (VP Marketing) |  |  | Total budget ($) | 120000
Report date | 2026-11-07 |  |  | Spent to date ($) | 70000
Reporting period | Weekly |  |  | Schedule variance (pts) | -8
Current phase | Build |  |  | Cost index (CPI) | 0.89143
|  |  |  | Forecast at completion | 134615.3846
OVERALL STATUS
Overall status | Amber
Executive summary | The redesign is in the build phase and 52% complete against a plan of 60%. Content migration is running one week late because product pages need legal review. Budget is tracking slightly over. We need a decision on the launch date by Friday.
HEALTH BY AREA
Area | Status | Suggested |  |  | Notes and recovery action
Schedule | Amber | Amber |  |  | Content migration 1 week late. Contract writer added.
Budget | Amber | Amber |  |  | Writer adds $6,000, covered by contingency.
Scope | Green | (your judgment)
Quality | Green | (your judgment)
Resources | Amber | (your judgment) |  |  | Lead developer out 3 days next week.
MILESTONES
Milestone | Due date | Status | Flag
Design approved | 2026-10-17 | Done
Templates built | 2026-11-04 | Done
Content migrated | 2026-11-06 | In progress | OVERDUE
User testing | 2026-11-21 | Not started
Go live | 2026-12-12 | Not started
Overdue milestones | 1
DONE THIS PERIOD AND NEXT PERIOD
Done this period |  |  | Next period
Built 14 of 16 page templates |  |  | Finish the last 2 templates
Finished accessibility review |  |  | Clear legal review on product pages
Moved 120 of 210 pages to the new CMS |  |  | Book 8 users for testing
RISKS AND ISSUES
Description | Type | Impact | Owner | Due date | Action | Check
Legal review is slowing product page migration | Issue | High | Maya Chen | 2026-11-09 | Daily 15-minute review slot agreed with legal | OK
Search rankings may drop after launch | Risk | Medium | Sam Lee | 2026-12-07 | Map 301 redirects for all old URLs | OK
Payment page vendor update in the launch week | Risk | Medium |  |  |  | Needs owner/action
Open high-impact items | 1
DECISIONS OR HELP NEEDED
Decision needed |  |  | From | By | Status
Keep the launch date or move it 1 week |  |  | Daniel Ortiz | 2026-11-11 | Open
Escalation check | OK

## Trend
Status Trend
Add one row per report. Variance and cost index are calculated.
Report date | Overall status | Planned % | Actual % | Budget ($) | Spent ($) | Schedule var (pts) | Cost index | Comment
2026-10-17 | Green | 35% | 36% | 120000 | 50000 | 1 | 0.864 | On plan
2026-10-24 | Green | 45% | 43% | 120000 | 58000 | -2 | 0.88966 | Templates started
2026-10-31 | Amber | 52% | 47% | 120000 | 64000 | -5 | 0.88125 | Legal review delay
2026-11-07 | Amber | 60% | 52% | 120000 | 70000 | -8 | 0.89143 | Contract writer added